## INSTRUCTIONS
About this Form: This form is used to gather all of the required information specific to the migrating client. This information will be used to complete required forms and tickets for the migration project. Descriptions of each item and where to locate the information is provided below. Enter the value for each item in column B on the Client Information tab. If the item is not applicable, enter N/A in column B OR if the information has not yet been confirmed (is still unknown), enter TBD (To Be Determined) in column B. No field should be left blank. Items on the Client Information tab in PURPLE font are used for Certification and must contain information.
Item | Description | Where to Locate Information
MIGRATION DATE | The Go-Live date for the client migration. If this date changes, update column B and enter supporting notes in column E. | Debit Migrations Schedule_CA Working Copy; Debit Migrations Schedule tab, column A | Go-Live
FINANCIAL INSTITUTION NAME | The client name as listed in Entity 360 | Debit Migrations Schedule_CA Working Copy; Debit Migrations Schedule tab, column B Institution Name
ENTITY ID | Entity ID of the Financial Institution from Entity 360 | Debit Migrations Schedule_CA Working Copy; Debit Migrations Schedule tab, column B - in parentheses ( ) following the Institution Name
ADDRESS | Address of the Financial Institution | Entity 360
CITY | City of the Financial Institution | Entity 360
STATE | State of the Financial Institution | Entity 360
ZIP CODE | Zip Code of the Financial Institution | Entity 360
PHONE # | Phone # of the Financial Institution | Entity 360 or obtain from client on Kickoff Call
PROJECT COORDINATOR | The Debit Card Analyst assigned as the Project Coordinator | Debit Migrations Schedule_CA Working Copy; Debit Migrations Schedule tab, column C
CERTIFICATION REQUIRED (Yes or No) | All third party cores should require certification | Debit Migrations Schedule_CA Working Copy; Debit Migrations Schedule tab, column L
CERTIFICATION COORDINATOR | Assigned Certification Coordinator | Will be Mike Veierstahler, until notified otherwise
FI PRIMARY CONTACT NAME | Primary Contact Name at the Financial Institution | Debit Migrations Approved Clients; Active List tab, column K (Client Primary Contact)
FI PRIMARY CONTACT PHONE | Primary Contact Phone at the Financial Institution | Debit Migrations Approved Clients; Active List tab, column M (Phone #)
FI PRIMARY CONTACT EMAIL | Primary Contact Email at the Financial Institution | Debit Migrations Approved Clients; Active List tab, column N (Email)
CORE PROCESSOR | Name of the Core Processor for the Financial Institution | Debit Migrations Approved Clients; Active List tab, column F (Core Provider)
CORE CONTACT NAME | Core Contact Name | Requested from FI in the Introduction Email
CORE CONTACT EMAIL | Core Contact Email | Requested from FI in the Introduction Email
THIRD PARTY VENDOR NAME | Name of Third Party Vendor if applicable | Ask on the Kickoff Call
THIRD PARTY VENDOR EMAIL | Third Party Vendor Email if applicable | Ask on the Kickoff Call
THIRD PARTY VENDOR PHONE | Third Party Vendor Phone if applicable | Ask on the Kickoff Call
IG GROUP NAME (if applicable) | If the FI is a member of a League enter the group name | Debit Migrations Schedule_CA Working Copy; Debit Migrations Schedule tab, column K (In-house / Data Center /League)
LEAGUE CONTACT | The name of the contact at Envisant or Leverage. | If applicable
CLIENT RELATIONSHIP MANAGER | Relationship Manager listed in entity 360; N/A if Envisant Client | Entity 360
APPLICATION ACCESS ANALYST | Assigned Application Access Analyst | Maqhsoom will assign upon request (generally Hari for Norcross)
DECONVERSION ANLYST | Assigned Deconversion Analyst | Debit Migrations Schedule_CA Working Copy; Debit Migrations Schedule tab, column Q (Deconversion/Core Analyst)
SETTLEMENT ANALYST | Assigned Settlement Analyst (4 weeks prior to migration date) | Assigned by Steve Wolniakowski when requested 4 weeks prior to migration date
INSTANT ISSUE (Yes or No) | Does the Financial Institution use Instant Issue? | Ask on the Kickoff Call
INSTANT ISSUE VENDOR | Which vendor is used for Instant Issue? | Ask the client on the Kickoff Call if applicable
WIZPROC (if applicable) | Needed if Instant Issue vendor codes and sends 382s directly to FIS | Find out from Client and Core or Certification Coordinator
CENTRAL CARD ISSUE VENDOR | Current card vendor (e.g., CardPro) | Ask on the Kickoff Call
ROUTING #/INSTITUTION ID | Routing Number (R&T) of the Financial Institution | Entity 360, Keys tab, ABA Number or Norcross Screenshots (End of Day) under Institution FRBABA
CURRENT PSEUDO ROUTING # (if applicable) | Pseudo Routing Number the Financial Institution is currently using on Norcross | Norcross Screenshots
CURRENT SWITCH | Switch the FI is located on prior to migration | Pre-filled, all Norcross clients are on FISB
NEW SWITCH | Switch the FI will be migrating to (may be the same as the current switch) | Pre-filled, all Norcross clients will stay on FISB
NODE | Node the FI will use post migration | Pre-filled, all Norcross clients will move to A7X
PROC ID/PROCESSOR NAME | Proc ID/Processor Name assigned to the FI | Will be entered by the Operations Coordinator upon receipt
SHARED PROC/CORE | If the FI uses a Shared PI Process with the Core | The Certification Coordinator will provide.
STAND-IN PROC (*HORIZON ONLY*) | Needed if the FI has a HORIZON Core. | Will be entered by the Operations Coordinator upon receipt
FI ID (Only valid for Norcross) | FI ID | Norcross Screenshots (BIN) under Inst ID.
BINs | BIN numbers and type of BIN | Norcross Screenshots (BIN) | 414255 SCREENSHOT
BIN LENGTH | Length of each BIN (can list multiple lengths is applicable) | Norcross Screenshots (BIN) | 414255 SCREENSHOT
AIMS ID | AIMS Billing ID (10 characters) | Will be entered by the Operations Coordinator upon receipt
LIMIT GROUP | Limit Group(s) for the Financial Institution | The Project Coordinator will define based on the Limits on the Completed Host_AP Configuration Form.
ENTITY NAME (DN) | The Entity Name set up in DataNavigator by USERADMIN | Will be entered by the Migration Wave Coordinator upon receipt from the USERADMIN team.
FX ID | The FX ID of the Financial Institution | Will be entered by the Migration Wave Coordinator upon receipt from the USERADMIN team. OR Norcross CardClient Schedule; Schedule tab, column Y (File Transmission_ID)
FX ID - CORE VENDOR (if applicable) | The FX ID of the Core Vendor - if applicable | Ask the Core for this information, request an ID if they need one using the same form. (Refer to Migration Guide)
CVV EXPIRATION DATE FORMAT | Date format used - MMYY (default) or YYMM | Norcross Screenshots
ACRO/IBM ID | 3 character alpha code assigned to the FI by Jenny Kline's group and used in Lotus Notes for Batch Maintenance and Batch Refresh and for Card Loads | Will be entered by the Operations Coordinator upon receipt
CUTOFF TIME | Assigned Cutoff Time | Norcross Screenshots "Institution Cut Off", "Time Adjust" / Always 18:30 CT for Mercury clients | End of Day screenshot (Cut off):
SEND ADVICE | Setting for the approvals and declines that go to the Core. Options are 0, 1 or 2. Default is 1 | Completed Host_AP Configuration Form, CEDROUT Send Advice Option (available after the Kickoff Call)
VRU ACTIVATION OPTIONS | Which options the FI will use for activation | Completed Host_AP Configuration Form
CARD ACTIVATION LINE (Domestic)) | Card Activation Line - Domestic phone number | Pre-filled - same for all Norcross Clients
CARD ACTIVATION LINE (International) | Card Activation Line - International phone number | Pre-filled - same for all Norcross Clients
LOST/STOLEN After Hours | Lost/Stolen After Hours phone number | Pre-filled - same for all Norcross Clients
STACK | Required for Database team if applicable | The Certification Coordinator will provide if applicable
TSAP IP ADDRESS | TSAP IP Address | Created by Certification Coordinator will update the field
TSAP PORT | TSAP Port | Created by Certification Coordinator will update the field
TSAP DEVICE/CIRCUIT ID | TSAP Device Circuit ID | Created by Certification Coordinator will update the field
TSAP PI | TSAP PI | Created by Certification Coordinator will update the field
TSAP CH | TSAP CHI | Created by Certification Coordinator will update the field
TSAP TANDEM-PORT | TSAP Tandem-Port | Created by Certification Coordinator will update the field
BATCH TRANSFER (Zipped/Unzipped) | Is the Batch Transfer zipped or unzipped? | Completed Host_AP Configuration Form (available after the Kickoff Call)
BATCH TRANSFER (Text/HTML) | Is the Batch Transfer Text or HTML format? | Completed Host_AP Configuration Form (available after the Kickoff Call)
APB4 (Yes or No) | Does the FI use APB4? | Completed Host_AP Configuration Form (available after the Kickoff Call)
PBF (Yes or No) | Does the FI use PBF? | Completed Host_AP Configuration Form (available after the Kickoff Call)
ONLINE MAINTENANCE/382 MESSAGES |  | Completed Host_AP Configuration Form (available after the Kickoff Call)
LOTUS NOTES UNIQUE ID - BATCH MAINTENANCE (APB4) | If not using Batch Maintenance File enter N/A | Will be provided by the Migration Wave Coordinator when the Lotus Notes Request is submitted if applicable.
LOTUS NOTES UNIQUE ID - BALANCE REFRESH FILE (PBF) | If not using Balance Refresh File enter N/A | Will be provided by the Migration Wave Coordinator when the Lotus Notes Request is submitted if applicable.
POSTING FILE FORMAT 28 OR ISO USER FILE | Does the FI use Format 28 or the ISO User File? | Completed Host_AP Configuration Form (available after the Kickoff Call)
ISSUING NETWORKS | List the Issuing Networks | Completed Host_AP Configuration Form (available after the Kickoff Call)
ACQUIRING NETWORKS | List the Acquiring Networks | Completed Host_AP Configuration Form (available after the Kickoff Call)
SCORECARD/LOYALTY (Yes or No) | Does the FI use Scorecard or Loyalty? | Email to James Horn (email template)
SCORECARD PROGRAM ID | Program ID for Scorecard/Loyalty (for CIMS form) | Norcross Screenshots
SCORECARD AGENT ID | Agent ID for Scorecard/Loyalty (for CIMS form) | Norcross Screenshots
SCORECARD CORP ID | Corp ID for Scorecard/Loyalty (for CIMS form) | Norcross Screenshots
SCORECARD ASSOCIATION ID | Association ID for Scorecard/Loyalty (for CIMS form) | Norcross Screenshots
SECURLOCK PRODUCTS | What SecurLOCK products does the FI use? | Emtity 360 > Products and Applications
FRAUD CONTACT GROUP EMAIL (CLIENT) | Group email address required for the New Fraud Config Wave Sheet. | Project Coordinator will request from the Fion Kickoff Call Summary Email
3D SECURE (Yes or No) | Does the FI have 3D Secure? | Entity 360 > Products and Applications > Applications - 3D Secure Services
ARB (Yes or No) | Does the client have ARB? | Norcross Screenshots "Verify if FI participates in ARB Rules." If active rules are listed = YES | 7. Verify if FI participates in ARB rules.:
FastTrack (Yes or No) | Does the client use Sign & Earn? | Entity 360 > Products and Applications - FastTrack or on the "List"
Mobile Banking (Yes or No) | Does the client have Mobile Banking product? | Entity 360 > Products and Applications - FIS Mobile Banking Services
DEBIT, CREDIT OR BOTH | Does the FI have Debit Cards Only, Credit Cards Only or both Debit and Credit Cards? If both D and C are listed in column F on the extract enter BOTH. | Completed Host_AP Configuration Form (available after the Kickoff Call)
CARD TYPES | Assigned Card Types (ATM, Debit, Credit) | Completed Host_AP Configuration Form (available after the Kickoff Call) | Apcnfcom
CARD COUNT (ACTIVE) | Active Card Count | Available after the Initial Card Load
PLANVIEW ID=PV | Planview Project Number for recording project time | One PV ID per Migration Wave
CREQ# | Internal CREQ number assigned to this FI migration. | SNOW CREQ assigned to the Project Coordinator | INTERNAL CREATED TICKET ID CREATED BEFORE 30 days

## Client Information
This form is used to gather all of the required information specific to the migrating client. This information will be used to complete required forms and tickets for the migration project. Descriptions of each item and where to locate the information is provided below. Enter the value for each item in column B on the Client Information tab. If the item is not applicable, enter N/A in column B OR if the information has not yet been confirmed (is still unknown), enter TBD (To Be Determined) in column B. No field should be left blank.
Item | Client Setting/Value | Entered By | Validated By | Notes
MIGRATION DATE | 2025-11-26
FINANCIAL INSTITUTION NAME | xxxxyyyyyy
ENTITY ID | 123ABX007
ADDRESS | Karapakkam
CITY | Chennai
STATE | Tamil Nadu
ZIP CODE | 600117
PHONE # | 9911991100
PROJECT COORDINATOR | Sam
CERTIFICATION REQUIRED (Yes or No) | Yes
CERTIFICATION COORDINATOR
FI PRIMARY CONTACT NAME
FI PRIMARY CONTACT PHONE
FI PRIMARY CONTACT EMAIL
CORE PROCESSOR
CORE CONTACT NAME
CORE CONTACT EMAIL
THIRD PARTY VENDOR NAME
THIRD PARTY VENDOR EMAIL
THIRD PARTY VENDOR PHONE
IG GROUP NAME (if applicable)
LEAGUE CONTACT
CLIENT RELATIONSHIP MANAGER
APPLICATION ACCESS ANALYST
DECONVERSION ANALYST
SETTLEMENT ANALYST
INSTANT ISSUE (Yes or No)
INSTANT ISSUE VENDOR
WIZPROC (if applicable)
CENTRAL CARD ISSUE VENDOR
ROUTING #/INSTITUTION ID
CURRENT PSEUDO ROUTING # (if applicable)
CURRENT SWITCH | FISB | Default | Default
NEW SWITCH | FISB | Default | Default
NODE | A7X | Default | Default
PROC ID / PROCESSOR NAME
SHARED PROC/CORE
STAND-IN PROC (*HORIZON ONLY*)
FI ID (Only valid for Norcross)
BINs |  |  |  | See BIN Details Tab for additional details for each BIN
BIN LENGTH |  |  |  | See BIN Details Tab for additional details for each BIN
AIMS ID
LIMIT GROUP
ENTITY NAME (DN)
FX ID
FXID for Core Vendor (if applicable)
CVV EXPIRATION DATE FORMAT
ACRO/IBM ID
CUTOFF TIME | 18:00 CT * | Default | Default | *18:30 CT if Mercury Core
SEND ADVICE
VRU ACTIVATION OPTIONS
CARD ACTIVATION LINE (Domestic) | 855.485.7039 | Default | Default
CARD ACTIVATION LINE (International) | 501.725.9278 (Collect) | Default | Default
LOST STOLEN AFTER HOURS (Hotcarding) | 800.500.1044 | Default | Default
STACK |  |  |  | *to be entered by Certification Coordinator
TSAP IP ADDRESS |  |  |  | *to be entered by Certification Coordinator
TSAP PORT |  |  |  | *to be entered by Certification Coordinator
TSAP DEVICE/CIRCUIT ID |  |  |  | *to be entered by Certification Coordinator
TSAP PI |  |  |  | *to be entered by Certification Coordinator
TSAP CH |  |  |  | *to be entered by Certification Coordinator
TSAP TANDEM-PORT |  |  |  | *to be entered by Certification Coordinator
BATCH TRANSFER (Zipped/Unzipped)
BATCH TRANSFER (Text/HTML)
APB4 (Yes or No)
PBF (Yes or No)
ONLINE MAINTENANCE/382 MESSAGES
LOTUS NOTES UNIQUE ID - BATCH MAINTENANCE (APB4)
LOTUS NOTES UNIQUE ID - BALANCE REFRESH FILE (PBF)
POSTING FILE FORMAT 28 OR ISO USER FILE
ISSUING NETWORKS
ACQUIRING NETWORKS
SCORECARD/LOYALTY (Yes or No)
SCORECARD PROGRAM ID
SCORECARD AGENT ID
SCORECARD CORP ID
SCORECARD ASSOCIATION ID
SECURLOCK PRODUCTS
FRAUD CONTACT GROUP EMAIL (CLIENT)
3D SECURE (Yes or No)
ARB (Yes or No)
FastTrack (Yes or No)
Mobile Banking (Yes or No)
DEBIT, CREDIT OR BOTH
CARD TYPES
CARD COUNT (ACTIVE)
PLANVIEW ID
CREQ#

## Ticket Tracker
TICKET TRACKER
DEBIT MIGRATION TICKETS
Ticket / Request Name | Week Due | Ticket Number/Request ID | Date Submitted | Entered By | Validated By | Notes
Internal CREQ for Migration Project | ASD - 30 days
DRC Resource Request (RITM) | Week 13
Entity (DN) Form (Email) | Week 12
FXID Request (Email) | Week 12
FXID for Vendor/Core Request (Email) (if applicable) | Week 12
Network Request (CREQ) | Week 9
Pre-Add Offline(RITM) | Week 8
Lotus Notes Batch Transfer - Batch Maintenance (APB4) (if applicable)(Lotus Notes) | Week 8
Lotus Notes Batch Transfer - Balance Refresh File (PBF) (if applicable)(Lotus Notes) | Week 8
Pre-Add Online (RITM) | Week 6
Mobile Implementations (if applicable) (CREQ) | Week 6
ICM Deconversion (RITM) | Week 6
Hotcard (RITM) | Week 6
SecurLOCK (CREQ) | Week 5
Go-Live Request (RITM) | Week 4
MOVEit Production Control (CH) | Week 3
ABU (Mastercard BINs only) (IN) | Week 3
AP Print Posting File (RITM) | Week 3
Proc Ops Maintenance Request (RITM) | Week 2
ARB Rules to SLB (RITM) | Week 2
EPSI (RITM) | Week 1
FireCall Audit (WEB) | Week 1
Metadata Override Configuration (if applicable) | LIVE DAY
CERTIFICATION / NETWORK TICKETS
Ticket/ Request Name | Week Due | Ticket Number/Request ID | Date Submitted | Entered By | Validated By | Notes
NAT / Firewall /WIZPROC Request (if applicable) | Week 10
NSR Request (if applicable)
Offline and Online Cert Files for the FI (email)
DECONVERSION TICKETS (Deconversion Analysts)
Ticket / Request Name | Week Due | Ticket Number/Request ID | Date Submitted | Entered By | Validated By | Notes
Bank Access (CREQ) - HORIZON Core only | Week 3 |  |  |  |  | Debit - Core Implementations
Card Stock Update (RITM) - HORIZON/Non HORIZON Core | Week 3 |  |  |  |  | EFT Norcross Production Support
FTP Site/User Creation (RITM) - HORIZON/Non-HORIZON Core | Week 3 |  |  |  |  | ATL EFT Operations
DC Operation Resource Assignment (RITM) - HORIZON Core only | Week 1 |  |  |  |  | HORIZON DC Security & AIM
Transfer Profiles Add/Delete (RITM)- HORIZON Core only | Week 1 |  |  |  |  | HORIZON DC Security & AIM
Request HORIZON Password (RITM) - HORIZON Core only | Week 1 |  |  |  |  | HORIZON DC Security & AIM
IP Deletion (RITM) - Non-HORIZON Core | Post Migration Day 3 or 4 |  |  |  |  | EFT Norcross Production Support
APPLICATION ACCESS TICKETS
Ticket / Request Name | Week Due | Ticket Number/Request ID | Date Submitted | Entered By | Validated By | Notes
IdP Firm Build Request (RITM) | Week 7
Debit Insights Add (RITM) *N/A for Envisant customers | Week 5
Custom IdP Profiling (RITM) *If required | Week 4
DRC Access Request (RITM) | Week 4
Vision 4 (CS) *If applicable | Week 4
eAccess/CARF (CS) | Week 2
MOVEit - ETG Questionnaire *if folder setup required
Issues, Corrections and Post Go-Live Tickets
Ticket Reason | Ticket Type | Ticket Number | Date Submitted | Entered By | Validated By | Notes

## BIN Details
BIN DETAILS
BIN Number | Debit or Credit | Type of Card | Networks | Product Line of Card | Expiration Life Cycle | BIN Length | PAN Length | Reissue Lead Time
Note on B2: Select Debit or Credit
Note on C2: Select the Card type from the drop-down list.
Note on D2: Enter all networks associated with this BIN.
Note on F2: Enter the card life cycle in years (1,2,3,4,5) OR non-expiring.
Note on I2: When will the new card be issued in relation to the expiration date of the current card. (usually 30 days)

## Migration Tasks Tracker
Scheduled Migration Date (MD) | Analyst Start Date (ASD) | Revised Migration Date (if applicable) | Create CREQ and assign to Project Coordinator (Operations) | Create FI Project Folder (Operations) | Request AIMS ID (Operations) | Request PROC ID (Operations) | Request Norcross Screenshots (Operations) | Create Initial Project Artifacts (Operations) | Submit DRC Resource Request Ticket (Operations) | FastTrack Email Notification Due Date (Operations) | Send Introduction Email | Date Introduction Email Sent | Client Migration Information Form Review/Update | Host_AP Configuration Form Update | Client Migration Plan Workbook Review/Update | Migration Validation Document Confirmation | Lessons Learned Worksheet Confirmation | Entity Form for Clients (Wave) | FTP (FXID) Access Request Email (Wave) | Create Kickoff Call Presentation | Kickoff Call Invite Due | Kickoff Call | Kickoff Call Summary Email Due | Schedule Weekly Client Status Calls | 3D Secure BIN Validation Email Due (Wave) | Forms Due from FI: Host_AP Config and Funds Movement | Training Registration Email Due Date | Network Licensing Request Ticket Due Date (Wave) | Forms Due from FI: Contacts for Transmissions, Contacts for PROCS, FIS Academy User Setup | Transmission Contacts Notification | PROCs Contact Notification | Pre-Add Forms Preparation Begins | Submit FIS Academy User Setup Form to Learning Solutions | Confirm Network Licensing paperwork was sent to FI (Wave) | Submit Pre-Add Offline Ticket | Lotus Notes Request Due Date (Wave) | Schedule Internal Go-Live Playbook Meeting | IVR Number Notification Email Due Date | Confirm Pre-Add Offline Tasks Accepted | Cash Management Emai Due | Go-Live Playbook Preparation Meeting | PaymentsOne Reports Email Due | Scorecard/Loyalty BIN Notification Email Due | Migration Validation Milestone 1 | Submit Pre-Add Online Ticket | Mobile Implementations Ticket Due Date | Form Due from FI: Authorized Signers Form | Submit ICM Deconversion Ticket | Hotcard Ticket Due Date (Wave) | CO-OP Notification Email | Add Go-Live Playbook to Client Migration Plan | Confirm FI has updated ARB Rules (on status call) | SecurLOCK Ticket Due Date (Wave) | Training Checkpoint | Confirm Network has submitted FI paperwork (Wave) | Go-Live Forms Preparation | Internal Playbook Creation | AIMS Billing Email Due Date | Settlement Resource Request Email Due Date (Wave) | Card Load Meeting Invitations (2) | Internal Bridge Line Invitation | Go-Live Ticket Due Date | MOVEit Files and Reports Change Request Due Date (Wave) | Migration Validation Milestone 2 | ABU Ticket Due Date | Submit AP Print Posting File Ticket | COOP Control Card Notification Email Due | Proc Ops Maintenance Ticket (WAVE) | Chargeback Email Notification | Confirm Database Online Table Load (Email) | Pre-Live Instructions Email Due Date | Go-Live Playbook Activated | ARB to SLB Rules Ticket Due | CREQ: Close Fulfillment CRQTASK | EPSI Ticket Due Date | GO-LIVE CHECKPOINT | CREQ: Close Client Validation CRQTASK | Initial Card Load Meeting | Final Card Load Meeting | ARB to SLB Rules Load Confirmation Email | Firecall Audit Request to Proc Ops (Wave) | Migration Validation Milestone 3 | Update Metadata Override Configuration if BIN < or > 16 digits | Monitor Live Day Traffic | Migration Update Email Due Date | Client Confirmation Form Review Meeting with Client | CREQ: Close Go-Live CRQTASK | CREQ: Reassign the Review & Submit Billing CRQTASK | Monitor/Resolve Outstanding Issues | Internal Turnover to FIS Client Support Email Due Date | Client Turnover Notification | Lessons Learned Worksheet Due Date | CREQ: Close Review & Submit Billing CRQTASK (Operations) | Project Cleanup | Close Planview Project (Operations)
2026-02-02 | 2025-11-03 | (PILOT) | 2025-10-04 | 2025-10-04 | 2025-10-04 | 2025-10-04 | 2025-10-04 | 2025-10-04 | 2025-11-03 | 2025-11-03 | 2025-11-10 |  | 2025-11-10 | 2025-11-10 | 2025-11-10 | 2025-11-10 | 2025-11-10 | 2025-11-10 | 2025-11-10 | 2025-11-10 | 2025-11-17 |  | 1899-12-31 | 2025-11-17 | 2025-11-24 | 2025-11-24 | 2025-11-24 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-01 | 2025-12-08 | 2025-12-08 | 2025-12-08 | 2025-12-08 | 2025-12-15 | 2025-12-15 | 2025-12-15 | 2025-12-15 | 2025-12-15 | 2025-12-15 | 2025-12-22 | 2025-12-22 | 2025-12-22 | 2025-12-22 | 2025-12-22 | 2025-12-22 | 2025-12-22 | 2025-12-22 | 2025-12-22 | 2025-12-29 | 2025-12-29 | 2025-12-29 | 2025-12-29 | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-27 | 2026-01-30 | 2026-01-30 | 2026-01-30 | 2026-01-26 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-04 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-11 | 2026-02-11 | 2026-02-16 | 2026-02-16 | 2026-03-04 | 2026-03-19
2026-03-16 | 2025-12-15 | (PILOT) | 2025-11-15 | 2025-11-15 | 2025-11-15 | 2025-11-15 | 2025-11-15 | 2025-11-15 | 2025-12-15 | 2025-12-15 | 2025-12-22 |  | 2025-12-22 | 2025-12-22 | 2025-12-22 | 2025-12-22 | 2025-12-22 | 2025-12-22 | 2025-12-22 | 2025-12-22 | 2025-12-29 |  | 1899-12-31 | 2025-12-29 | 2026-01-05 | 2026-01-05 | 2026-01-05 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-10 | 2026-03-13 | 2026-03-13 | 2026-03-13 | 2026-03-09 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-18 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-25 | 2026-03-25 | 2026-03-30 | 2026-03-30 | 2026-04-15 | 2026-04-30
2026-04-06 | 2026-01-05 |  | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2025-12-06 | 2026-01-05 | 2026-01-05 | 2026-01-12 |  | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-12 | 2026-01-19 |  | 1899-12-31 | 2026-01-19 | 2026-01-26 | 2026-01-26 | 2026-01-26 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-31 | 2026-04-03 | 2026-04-03 | 2026-04-03 | 2026-03-30 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-08 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-15 | 2026-04-15 | 2026-04-20 | 2026-04-20 | 2026-05-06 | 2026-05-21
2026-04-13 | 2026-01-12 |  | 2025-12-13 | 2025-12-13 | 2025-12-13 | 2025-12-13 | 2025-12-13 | 2025-12-13 | 2026-01-12 | 2026-01-12 | 2026-01-19 |  | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-19 | 2026-01-26 |  | 1899-12-31 | 2026-01-26 | 2026-02-02 | 2026-02-02 | 2026-02-02 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-09 | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-02-23 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-07 | 2026-04-10 | 2026-04-10 | 2026-04-10 | 2026-04-06 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-15 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-22 | 2026-04-22 | 2026-04-27 | 2026-04-27 | 2026-05-13 | 2026-05-28
2026-05-11 | 2026-02-09 |  | 2026-01-10 | 2026-01-10 | 2026-01-10 | 2026-01-10 | 2026-01-10 | 2026-01-10 | 2026-02-09 | 2026-02-09 | 2026-02-16 |  | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-16 | 2026-02-23 |  | 1899-12-31 | 2026-02-23 | 2026-03-02 | 2026-03-02 | 2026-03-02 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-05 | 2026-05-08 | 2026-05-08 | 2026-05-08 | 2026-05-04 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-13 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-20 | 2026-05-20 | 2026-05-25 | 2026-05-25 | 2026-06-10 | 2026-06-25
2026-06-01 | 2026-03-02 |  | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-01-31 | 2026-03-02 | 2026-03-02 | 2026-03-09 |  | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-09 | 2026-03-16 |  | 1899-12-31 | 2026-03-16 | 2026-03-23 | 2026-03-23 | 2026-03-23 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-26 | 2026-05-29 | 2026-05-29 | 2026-05-29 | 2026-05-25 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-03 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-10 | 2026-06-10 | 2026-06-15 | 2026-06-15 | 2026-07-01 | 2026-07-16
2026-06-08 | 2026-03-09 |  | 2026-02-07 | 2026-02-07 | 2026-02-07 | 2026-02-07 | 2026-02-07 | 2026-02-07 | 2026-03-09 | 2026-03-09 | 2026-03-16 |  | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-16 | 2026-03-23 |  | 1899-12-31 | 2026-03-23 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-02 | 2026-06-05 | 2026-06-05 | 2026-06-05 | 2026-06-01 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-10 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-17 | 2026-06-17 | 2026-06-22 | 2026-06-22 | 2026-07-08 | 2026-07-23
2026-06-22 | 2026-03-23 |  | 2026-02-21 | 2026-02-21 | 2026-02-21 | 2026-02-21 | 2026-02-21 | 2026-02-21 | 2026-03-23 | 2026-03-23 | 2026-03-30 |  | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-03-30 | 2026-04-06 |  | 1899-12-31 | 2026-04-06 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-16 | 2026-06-19 | 2026-06-19 | 2026-06-19 | 2026-06-15 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-24 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-07-01 | 2026-07-01 | 2026-07-06 | 2026-07-06 | 2026-07-22 | 2026-08-06
2026-06-29 | 2026-03-30 |  | 2026-02-28 | 2026-02-28 | 2026-02-28 | 2026-02-28 | 2026-02-28 | 2026-02-28 | 2026-03-30 | 2026-03-30 | 2026-04-06 |  | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-06 | 2026-04-13 |  | 1899-12-31 | 2026-04-13 | 2026-04-20 | 2026-04-20 | 2026-04-20 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-23 | 2026-06-26 | 2026-06-26 | 2026-06-26 | 2026-06-22 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-07-01 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-08 | 2026-07-08 | 2026-07-13 | 2026-07-13 | 2026-07-29 | 2026-08-13
2026-07-06 | 2026-04-06 |  | 2026-03-07 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 2026-03-07 | 2026-04-06 | 2026-04-06 | 2026-04-13 |  | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-13 | 2026-04-20 |  | 1899-12-31 | 2026-04-20 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-30 | 2026-07-03 | 2026-07-03 | 2026-07-03 | 2026-06-29 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-08 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-15 | 2026-07-15 | 2026-07-20 | 2026-07-20 | 2026-08-05 | 2026-08-20
2026-07-20 | 2026-04-20 |  | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-03-21 | 2026-04-20 | 2026-04-20 | 2026-04-27 |  | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-04-27 | 2026-05-04 |  | 1899-12-31 | 2026-05-04 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-14 | 2026-07-17 | 2026-07-17 | 2026-07-17 | 2026-07-13 | 2026-07-20 | 2026-07-20 | 2026-07-20 | 2026-07-22 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-29 | 2026-07-29 | 2026-08-03 | 2026-08-03 | 2026-08-19 | 2026-09-03
2026-07-27 | 2026-04-27 |  | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-03-28 | 2026-04-27 | 2026-04-27 | 2026-05-04 |  | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-04 | 2026-05-11 |  | 1899-12-31 | 2026-05-11 | 2026-05-18 | 2026-05-18 | 2026-05-18 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-20 | 2026-07-20 | 2026-07-20 | 2026-07-20 | 2026-07-20 | 2026-07-21 | 2026-07-24 | 2026-07-24 | 2026-07-24 | 2026-07-20 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-29 | 2026-08-03 | 2026-08-03 | 2026-08-03 | 2026-08-05 | 2026-08-05 | 2026-08-10 | 2026-08-10 | 2026-08-26 | 2026-09-10
2026-08-03 | 2026-05-04 |  | 2026-04-04 | 2026-04-04 | 2026-04-04 | 2026-04-04 | 2026-04-04 | 2026-04-04 | 2026-05-04 | 2026-05-04 | 2026-05-11 |  | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-11 | 2026-05-18 |  | 1899-12-31 | 2026-05-18 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-20 | 2026-07-20 | 2026-07-20 | 2026-07-20 | 2026-07-20 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-28 | 2026-07-31 | 2026-07-31 | 2026-07-31 | 2026-07-27 | 2026-08-03 | 2026-08-03 | 2026-08-03 | 2026-08-05 | 2026-08-10 | 2026-08-10 | 2026-08-10 | 2026-08-12 | 2026-08-12 | 2026-08-17 | 2026-08-17 | 2026-09-02 | 2026-09-17
2026-08-17 | 2026-05-18 |  | 2026-04-18 | 2026-04-18 | 2026-04-18 | 2026-04-18 | 2026-04-18 | 2026-04-18 | 2026-05-18 | 2026-05-18 | 2026-05-25 |  | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-05-25 | 2026-06-01 |  | 1899-12-31 | 2026-06-01 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-20 | 2026-07-20 | 2026-07-20 | 2026-07-20 | 2026-07-20 | 2026-07-20 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-08-03 | 2026-08-03 | 2026-08-03 | 2026-08-03 | 2026-08-03 | 2026-08-10 | 2026-08-10 | 2026-08-10 | 2026-08-10 | 2026-08-10 | 2026-08-11 | 2026-08-14 | 2026-08-14 | 2026-08-14 | 2026-08-10 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-19 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-26 | 2026-08-26 | 2026-08-31 | 2026-08-31 | 2026-09-16 | 2026-10-01
2026-08-24 | 2026-05-25 |  | 2026-04-25 | 2026-04-25 | 2026-04-25 | 2026-04-25 | 2026-04-25 | 2026-04-25 | 2026-05-25 | 2026-05-25 | 2026-06-01 |  | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-01 | 2026-06-08 |  | 1899-12-31 | 2026-06-08 | 2026-06-15 | 2026-06-15 | 2026-06-15 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-20 | 2026-07-20 | 2026-07-20 | 2026-07-20 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-08-03 | 2026-08-03 | 2026-08-03 | 2026-08-03 | 2026-08-03 | 2026-08-10 | 2026-08-10 | 2026-08-10 | 2026-08-10 | 2026-08-10 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-18 | 2026-08-21 | 2026-08-21 | 2026-08-21 | 2026-08-17 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-26 | 2026-08-31 | 2026-08-31 | 2026-08-31 | 2026-09-02 | 2026-09-02 | 2026-09-07 | 2026-09-07 | 2026-09-23 | 2026-10-08
2026-08-31 | 2026-06-01 |  | 2026-05-02 | 2026-05-02 | 2026-05-02 | 2026-05-02 | 2026-05-02 | 2026-05-02 | 2026-06-01 | 2026-06-01 | 2026-06-08 |  | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-08 | 2026-06-15 |  | 1899-12-31 | 2026-06-15 | 2026-06-22 | 2026-06-22 | 2026-06-22 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-06 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-20 | 2026-07-20 | 2026-07-20 | 2026-07-20 | 2026-07-20 | 2026-07-20 | 2026-07-20 | 2026-07-20 | 2026-07-20 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-08-03 | 2026-08-03 | 2026-08-03 | 2026-08-03 | 2026-08-03 | 2026-08-03 | 2026-08-10 | 2026-08-10 | 2026-08-10 | 2026-08-10 | 2026-08-10 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-25 | 2026-08-28 | 2026-08-28 | 2026-08-28 | 2026-08-24 | 2026-08-31 | 2026-08-31 | 2026-08-31 | 2026-09-02 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-09 | 2026-09-09 | 2026-09-14 | 2026-09-14 | 2026-09-30 | 2026-10-15
2026-09-21 | 2026-06-22 |  | 2026-05-23 | 2026-05-23 | 2026-05-23 | 2026-05-23 | 2026-05-23 | 2026-05-23 | 2026-06-22 | 2026-06-22 | 2026-06-29 |  | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-06-29 | 2026-07-06 |  | 1899-12-31 | 2026-07-06 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-20 | 2026-07-20 | 2026-07-20 | 2026-07-20 | 2026-07-20 | 2026-07-20 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-08-03 | 2026-08-03 | 2026-08-03 | 2026-08-03 | 2026-08-03 | 2026-08-03 | 2026-08-10 | 2026-08-10 | 2026-08-10 | 2026-08-10 | 2026-08-10 | 2026-08-10 | 2026-08-10 | 2026-08-10 | 2026-08-10 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-31 | 2026-08-31 | 2026-08-31 | 2026-08-31 | 2026-08-31 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-15 | 2026-09-18 | 2026-09-18 | 2026-09-18 | 2026-09-14 | 2026-09-21 | 2026-09-21 | 2026-09-21 | 2026-09-23 | 2026-09-28 | 2026-09-28 | 2026-09-28 | 2026-09-30 | 2026-09-30 | 2026-10-05 | 2026-10-05 | 2026-10-21 | 2026-11-05
2026-10-05 | 2026-07-06 |  | 2026-06-06 | 2026-06-06 | 2026-06-06 | 2026-06-06 | 2026-06-06 | 2026-06-06 | 2026-07-06 | 2026-07-06 | 2026-07-13 |  | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-13 | 2026-07-20 |  | 1899-12-31 | 2026-07-20 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-08-03 | 2026-08-03 | 2026-08-03 | 2026-08-03 | 2026-08-03 | 2026-08-03 | 2026-08-10 | 2026-08-10 | 2026-08-10 | 2026-08-10 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-31 | 2026-08-31 | 2026-08-31 | 2026-08-31 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-21 | 2026-09-21 | 2026-09-21 | 2026-09-21 | 2026-09-21 | 2026-09-28 | 2026-09-28 | 2026-09-28 | 2026-09-28 | 2026-09-28 | 2026-09-29 | 2026-10-02 | 2026-10-02 | 2026-10-02 | 2026-09-28 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-07 | 2026-10-12 | 2026-10-12 | 2026-10-12 | 2026-10-14 | 2026-10-14 | 2026-10-19 | 2026-10-19 | 2026-11-04 | 2026-11-19
2026-10-19 | 2026-07-20 |  | 2026-06-20 | 2026-06-20 | 2026-06-20 | 2026-06-20 | 2026-06-20 | 2026-06-20 | 2026-07-20 | 2026-07-20 | 2026-07-27 |  | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-07-27 | 2026-08-03 |  | 1899-12-31 | 2026-08-03 | 2026-08-10 | 2026-08-10 | 2026-08-10 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-17 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-24 | 2026-08-31 | 2026-08-31 | 2026-08-31 | 2026-08-31 | 2026-08-31 | 2026-08-31 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-07 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-14 | 2026-09-21 | 2026-09-21 | 2026-09-21 | 2026-09-21 | 2026-09-21 | 2026-09-21 | 2026-09-28 | 2026-09-28 | 2026-09-28 | 2026-09-28 | 2026-09-28 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-05 | 2026-10-12 | 2026-10-12 | 2026-10-12 | 2026-10-12 | 2026-10-12 | 2026-10-13 | 2026-10-16 | 2026-10-16 | 2026-10-16 | 2026-10-12 | 2026-10-19 | 2026-10-19 | 2026-10-19 | 2026-10-21 | 2026-10-26 | 2026-10-26 | 2026-10-26 | 2026-10-28 | 2026-10-28 | 2026-11-02 | 2026-11-02 | 2026-11-18 | 2026-12-03
*Dates are the proposed migration waves for 2026 beginning 4/6/26
|  |  | ASD-30 days | ASD-30 days | ASD-30 days | ASD-30 days | ASD-30 days | ASD- 30 days | MD-13 weeks | MD-13 weeks (if applicable) | MD-12 weeks *On Monday* | {Enter actual date sent} | MD-12 weeks | MD-12 weeks | MD-12 weeks | MD-12 weeks | MD-12 weeks | MD-12 weeks | MD-12 weeks | MD-12 weeks | MD-12 weeks | MD-11 weeks Enter actual date scheduled/held | 1 business day after Kickoff Call | MD-11 weeks (If applicable) | MD-10 weeks | MD-10 weeks | MD-10 weeks (If applicable) | MD-9 weeks | MD-9 weeks (If applicable) | MD-9 weeks | MD-9 weeks (If applicable) | MD-9 weeks | MD-9 Weeks (If applicable) | MD-8 weeks | MD-8 weeks | MD-8 weeks | MD-8 weeks | MD-7 weeks | MD-7 weeks | MD-7 weeks | MD-7 weeks | MD-7 weeks | MD-7 weeks | MD-6 weeks | MD-6 weeks | MD-6 weeks (if applicable) | MD-6 weeks | MD-6 weeks | MD-6 weeks | MD-6 weeks (If applicable) | MD-6 weeks | MD-6 weeks (If applicable) | MD-5 weeks | MD-5 weeks (If applicable) | MD-5 weeks | MD-5 weeks | MD-4 weeks | MD-4 weeks | MD-4 weeks | MD-4 weeks | MD-4 weeks | MD-4 weeks | MD-3 weeks | MD-3 weeks | MD-3 weeks Mastercard Only | MD-3 weeks | MD-3 weeks | MD-2 weeks | MD-2 weeks | MD-2 weeks | MD-2 weeks; after the weekly call | MD-2 weeks | MD-2 weeks (If applicable) | MD-1 week | MD-1 week | MD-1 week | MD-1 week | MD-6 days | MD-3 days | MD-3 days | MD-3 days | MD-1 week | LIVE DAY - EARLY (If applicable) | LIVE DAY | LIVE DAY | MD+2 days | MD+1 week | MD+1 week | MD+1 week | MD+9 days | MD+9 days | MD+2 weeks | MD+2 weeks | MD+30 days | MD+45 days
*The tasks listed on this tab are for the Debit Migration team only*

## Limits
Group: (Enter Group ID)
Limit Usage | #Uses | Max Amt | Min Amt | Incrtmnt | Avail % | Reset At | On Days
WDR020 WD020U |  |  | 0 | 0.01 | 100% | 2:00 | SMTWTFS
WDR040 WD020U |  |  | 0 | 0.01 | 100% | 2:00 | SMTWTFS
PUR020 PU020U |  |  | 0 | 0.01 | 100% | 2:00 | SMTWTFS
PUR040 PU020U |  |  | 0 | 0.01 | 100% | 2:00 | SMTWTFS
AVD020 AD020U |  | 0.01 | 0 | 0.01 | 100% | 2:00 | SMTWTFS
AVD040 AD020U |  | 0.01 | 0 | 0.01 | 100% | 2:00 | SMTWTFS
TDB020 TD020U |  |  | 0 | 0.01 | 100% | 2:00 | SMTWTFS
TDB040 TD020U |  |  | 0 | 0.01 | 100% | 2:00 | SMTWTFS
DEP020 DP020U |  |  | 0 | 0.01 | 100% | 2:00 | SMTWTFS
DEP040 DP020U |  |  | 0 | 0.01 | 100% | 2:00 | SMTWTFS
UAV020 UA020U |  | 0.01 | 0 | 0.01 | 100% | 2:00 | SMTWTFS
AFT020 AF020U |  |  | 0 | 0.01 | 100% | 2:00 | SMTWTFS
AFT040 AF020U |  |  | 0 | 0.01 | 100% | 2:00 | SMTWTFS

## INTERNAL Issues Log
Internal Issues Log
Client Name: {FI NAME} (EID)
Issue ID# | Date Reported | Status | Category/Type | Impact | Product / Service | High Level Summary of the Issue or Question | Cardholder Impact? | Progress / Status Updates / Next Steps | Ticket #s | Reported By | Assigned Resource or Team | Resolution Target Date | Root Cause | Resolution | Date Resolved
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20
21
22
Note on A3: Unique number to identify the issue.
Note on B3: Date the issue was reported.
Note on C3: The current status of the issue. Update as necessary. Open: Issue reported or question submitted and in progress Escalated: Issue escalated to assignee or team for resolution Monitoring: Being monitored to see if it reoccurs. Resolved: Resolution implemented, issue closed or questions answered. Reopened: Previously closed or resolved, but has been reopened. Canceled: Not an issue, no longer needed; canceled by client.
Note on D3: Identify as an issue or a question.
Note on E3: Indicates the urgency of the issue. Critical: Show-stopper. No interim solution, issue requires immediate resolution before any project activities can continue. High: Interim solution available, issue requires resolution before specific project activities can continue. Medium: Interim solution available, project activities may continue, but issue requires resolution by a defined date. Low: Issue has minimal or no current impact on project activities, but priority could change if not resolved.
Note on F3: Enter the product or application impacted.
Note on G3: A description of the issue (or question) and the impact on the project.
Note on H3: Does this issue impact the cardholder?
Note on I3: Notes regarding resolution progress updates
Note on J3: Enter all ticket numbers submitted for resolution
Note on K3: Enter name of the person who reported the issue.
Note on L3: Enter name of the person or team this is assigned to
Note on M3: Enter expected resolution date.
Note on O3: Enter the details on what was done to resolve the issue.
Note on P3: Enter the date the issue was confirmed resolved by the client.

## DO WE NEED THESE (hidden)
AUTO CARD GENERATION | NO | FOUND IN P T
START CARD |  | Added by Rolaine - things that should be confirmed on kick off call
ABU |  | Added by Rolaine
DEBIT INSIGHTS |  | Added by Rolaine - To confirm witih Client
AUTO REISSUE EMV |  | Added by Rolaine
BIN LENGTH | 16 | FOUND IN P T
PROCESSOR ID | 0ANU | FOUND IN P T
SETTLEMENT | 7 DAYS | FOUND IN P T
CORP ID | 386050 | FOUND IN P T
MC ICA NUMBER | 4346 | FOUND IN P T
CIMS CARD SERVICE CODE | 101 | FOUND IN P T
MONTHS TO REISSUE | 36 | FOUND IN P T
EMV DEFAULT CARD STOCK CODE | XG080 | FOUND IN P T
C2V EXP DATE FORMAT | YYMM | FOUND IN P T
REPORTS | TYPE: TRANSMIT
REPORTS | SENT: Ereports
EXPIRATION DATE MISMATCH | Expiration date checking on All transactions
MEMBER NUMBER PARTICIPANT | No member number processing or embossing selected
VAU ID | 1153